## READ FIRST
The purpose of this Workplan is to help plan for and manage the transfer of a Model A fiscal sponsor project into a newly formed independent 501(c)(3) organization. Although all such transitions share common steps and this template is designed to capture them, each transition is unique. Thus, we recommend the parties work together to build a plan that speaks to their situation and then carefully manage it together. This Workplan can also be modified for instances where a Model A project is moving from one sponsor to another.

## Transition Workplan
Fiscally Sponsored Project Transition Plan
Fiscally Sponsored Project (FSP): NAME
Fiscal Sponsor: NAME
Target Transition Date: DATE
Tasks |  | Documents to be collected to support the Transition | Key Deliverable | Key Responsibility | Additional Participants | General Order of Occurance (1-3) | Target Date | Status Notes
General
| Document official notice of intent to separate per Fiscal Sponsorship Agreement |  | Documentation of notice | FSP or Sponsor |  | 1
| Finalize this Transition Out Workplan |  | Workplan | FSP & Sponsor |  | 1
| Participate in monthly transition check-ins |  |  | FSP & Sponsor |  | ongoing
Legal & Contractual
Legal Status | [7 empty] | It is critical enough time be given for inedpentent formation, developing policies, and securing 501(c)(3) status prior to full transition.
| Incorporate and register with attorney general and other regulatory bodies |  |  | FSP |  | 1
| File 1023 with IRS |  |  | FSP |  | 1
| Secure 501(c)(3) status |  |  | FSP |  | 3
Transfer Agreement
| Draft Asset Transfer Agreement | Various |  | Sponsor |  | 1
| Negotiate Asset Transfer Agreement |  |  | FSP & Sponsor |  | 2
| Execute Asset Transfer Agreement | Exit & Assets Transfer Agreement | Executed Asset Transfer Agreement | FSP & Sponsor |  | 3
Vendor Contracts | Establish a list of all currently active contracts which are in place (including terms of transition, termination expectations, and the scope of services and commitments) |  | List of currently active vendors | FSP & Sponsor |  | 1
| Determine the list of vendors that will be in place after the transfer and will provide services in the future |  |  | FSP |  | 2
| Prepare draft contracts, and negotiate the terms with the providers that will continue to provide services |  | Establish new vendor agreements | FSP |  | 3
| Issue notification notices to all vendors with whom services will no longer continue |  |  | Sponsor |  | 3
| Issue a letter to the vendors about the close of current agreement and expectations related to final billing |  | Close all current vendor agreements | Sponsor |  | 3
Insurance | Secure Insurance broker & clarify the insurance coverage needs | Current insurance coverage |  | FSP |  | 2
| Work with the Insurance agent to make sure organization is incorporated in all related policies |  |  | FSP |  | 3
| Remove organization from current insurance policies |  | Establish a new insurance coverage and close current one | Sponsor |  | 3
Program Partners | Review all current partners that will be providing programming services | List of current partners |  | FSP |  | 2
| Determine the terms of services that will be established with each of the partner after the transition |  |  | FSP |  | 3
| Finalize the agreements with all key partners that will be offering services |  | Establish new parner agreements | FSP |  | 3
| Issue a letter to the partners about the close of current agreement and expectations related to final billing |  | Close all current partnership agreements | Sponsor |  | 3
Leases | Document the list of current renters/review current lease agreement, and the terms of these agreements, and if they will be transitioned | List of current leases |  | Sponsor |  | 2
| Issue a letter to the landlord about the close of current agreement, expectations related to final billing and downpayments and transfer of current responsibilities |  | Transfer rent obligations | Sponsor |  | 3
Grants/ Contracts | Determine the list of grants/ contracts which will need to transition | Grants/Contracts Tracker |  | FSP & Sponsor |  | 2
| Notify funders/ customers about the transition |  |  | FSP & Sponsor |  | 3
| Follow-up with funders regarding transferring of funds processes |  |  | Sponsor |  | 3
| Send new paperwork to grantors, vendors, etc. |  | Transfer all ongoing grant and contract engagements | FSP |  | 3
Governance & Long-Term Operating Plan
| Identify and recruit additional board members (if appropriate) | Board List |  | FSP |  | 2
| Develop clear expectations of governance related roles & responsibilities |  | "Board Manual" | FSP |  | 2
Human Resources
| Review employees list that will be transitioning | Employee list |  | FSP |  | 2
| Define future benefits package and how it compares to the current benefits | Current benefit coverage |  | FSP |  | 3
| Clarify the plan how liabilities (e.g.PTO) will be addressed |  |  | FSP & Sponsor |  | 2
| Prepare termination letters |  | Termination Letters | Sponsor |  | 3
| Prepare and issue Hire Letters with Job Descriptions and benefits descriptions |  |  | FSP |  | 3
| Issue final paychecks and accrued vacation payouts |  |  | Sponsor |  | 3
| Terminate health and worker's comp insurances |  |  | Sponsor |  | 3
| Add employees to the payroll and benefit related accounts |  |  | FSP |  | 3
| Onboard employees into the HR related policies and procedures |  | New hire papework and employee orientations | FSP |  | 3
IT Vendors
| Assure all related software subscriptions are routed to new Debit Card / Payment process | List of current ongoing subscriptions |  | FSP |  | 3
| Train all staff in new system and documents protocols how to utilize future systems |  | All ongoing systems related charges are transfered | FSP |  | 3
Finance
FM system and Ongoing Accounting | Set up a new financial system for the organization | Organizational and grant related budgets |  | FSP |  | 2
| Review currently available assets and liabilities | Balance Sheet review |  | FSP & Sponsor |  | 2
| Establish a shared understanding how you will approach advances clearance, PPP, pre-paids, equipment and other balance sheet accounts |  |  | FSP & Sponsor |  | 2
| Collect final receivables |  |  | Sponsor |  | 3
| Determine cutover date (last day to pay bills and receive donations) |  |  | Sponsor |  | 2
| Submit final reimbursements or check requests |  |  | FSP |  | 3
| Issue final AP payments |  |  | Sponsor |  | 3
| Move all current donors and funders into the new donor management system (if that is changing) |  |  | FSP |  | 3
| Upload all vendors and customers into the new system |  |  | FSP |  | 3
Banking and Online Payment Platforms | Establish new bank account &/ Share information where the funds will be transfered |  |  | FSP |  | 3
| Review currently open Merchant Services accounts, and see if they will continue to be needed in the future |  |  | FSP |  | 2
| Set up/ update online services accounts (like NFG) |  | New accounts established/ ownership transfered | FSP |  | 3
| Communicate with all donors about the ways they could continue to contribute to the organization, and how to set up re-occurring contributions, and the value of their contribution to the organization |  |  | FSP |  | 3
| Submit final credit and Pex card reimbursements |  |  | FSP |  | 3
| Close currently open credit and PEX cards |  | All merchant and payment accounts closed | Sponsor |  | 3
Financial Management and Reporting | Project the assets (cash and net) that will be remaining as of the transfer date |  |  | FSP & Sponsor |  | 2
| Issue regular financial reports to review the progress regarding the spending and asset clearance |  |  | Sponsor |  | 2
| Complete the first agreed fund transfer |  | initial $ transfer | Sponsor |  | 2
| Complete final reconciliation of cash balances and balances |  |  | Sponsor |  | 3 |  | Final transfer of funds often occurs post transition date once all acounts reconcilled.
| Final transfer of funds |  | All assets and liabilities transfered | Sponsor |  | 3
| Produce final financial statement for review & sign off by executive leadership/ board (Reports will include Profit & Loss, Balance Sheet and additional supplementary schedules as needed) |  | Final financial reports shared | Sponsor |  | 3
Other | Inform the auditors (if applicable) about the upcoming changes in organization's assets |  |  | Sponsor |  | 2
Intellectual Property and Communications
| Transfer remaining IP assets & Data |  | If trademark, evidence of assignment with USPTO | Sponsor |  | 3
| Update staff on progress on Integration and the changes that they could expect |  |  | FSP & Sponsor |  | ongoing
| Complete exit interview |  |  | FSP & Sponsor |  | 3
| Report to Sponsor Board about the transition |  | Noted in Board Minutes | Sponsor |  | 2
Please add other things regarding communication plan here…
Transition Date: | [5 empty] | 3

## Preconditions for Transition
Pre-conditions for transition
Evidence of Good Standing and 501(c)(3) status
Set-up a Bank Account
Establish Financial system
Draft Policies and Procedures
Hire finance and accounting supports
Set up Payroll management system
Establish Contract templates
Purchase insurance (D&O, GL)
Board list
Executed Asset Transfer Agreement

## Questionnaire (hidden)
Project Transfer/Decommissioning Questionnaire
The following information will enable us to transfer or close your Movement Strategy Center project.
If some questions do not apply to your project, you can answer with N/A.
Please let us know if you have any questions.
Project Assets
Please list or describe:
FINANCIAL
1. Project Cash | [Financial reports provide this amount but be sure to review financial statements to make sure you don’t have any questions.]
2. Any marketable securities | Please list: ·
3. Any grants receivable dedicated exclusively to the Project | Please list: ·
4. Any accounts receivable exclusive to Project clients, and credit balances, advances, and deposits received or attributed exclusively to Project clients | Please list: ·
5. Income under any royalty agreements | Please list: ·
TANGIBLE PROPERTY
6. Any equipment, servers, computers, software installed on such computers (including the related licensing and support agreements for the use of such software), materials, supplies, furniture, or furnishings purchased with Project funds and used exclusively for the Project. | Please list any tangible property valued at >$500: ·
INTELLECTUAL PROPERTY
7. The Project’s copyrights, patents, trademarks, and logos: | Please list: ·
8. The Project’s website domain name, content, and URL | Please list: ·
9. Goodwill exclusive to the Project | Please list: ·
10. The Project’s social media accounts, including the following: | Please list: ·
CONTRACTS – please note that grants/contracts will need to be completed, cancelled, and/or reassigned.
11. Grant Agreements (funder, date, status) | Please list: ·
12. Web Hosting (provider, date) | Please list: ·
13. Other contracts (parties, date) | Please list: ·
14. Other agreements | Please list: ·
CLAIMS & LITIGATION
15. Any and all rights, claims, credits, causes of action, defenses, or settlement agreements to the extent arising from the Project Assets | Please list: ·
16. List any cases to be transferred from Movement Strategy Center to New Entity, if any | Please list: ·
17. Case files for any plaintiff-side litigation | Please list: ·
BOOKS & RECORDS
18. Program and financial records, donor list and contribution history, contact database, customer/client/member lists, correspondence, and other documents relating exclusively to the Project | Please list: ·
19. Newsletters, brochures, mailing lists, marketing materials, fundraising materials, handbooks, and other written materials used exclusively for the Project | Please list: ·
OTHER ASSETS (please describe)
20 | Please list: ·
Project Liabilities
1. All obligations under all contracts and grant agreements included in the Project Assets | Please list: ·
2. Any account payables related to the Project | Please list: ·
3. Other Project Liabilities, if any: | Please list: ·
Project Employees
1. List all project employees – both full and part-time. | Please list: ·

## Questions (hidden)
QUESTIONS | Answers
The level of reporting & notice during transition period to foundations? Who is responsible for providing notification? | Sponsor does not traditionally notify foundations. Projects will be responsible for send Sponsor reporting requests on grants. Sponsor can provide a breakdown of restricted assets so project knows what funding transitions to a new sponsor.
What is the process for mid-year v end of mid-year grant? What is the negotiation between new and old fiscal sponsors? Mid-cycle grants? | We encourage you to find a new sponsor as soon as possible, and we are happy to support any new grants to go directly to the new sponsor.
Is it possible to negotiate fees for new grants that land during transition? | This is possible, but it depends on timing, type of activity, etc.
How do we determine how much money is held until final transfer? | This is primarily a timing consideration. We definitely hold Workers Comp estimate until the close of the Workers Comp Audit.
Can I begin accepting funds (individual donors, grants, . . . ) at my new 501(c)3 before my exit date?
How is grant reporting happening after we exit?